EDMA — Week 1

Day-by-Day Execution Plan

March 17 — 21, 2026

Goal: Public testnet live with explorer and RPC by Friday

# Week 1 Objective

By end of day Friday, March 21, these must be live and accessible to anyone:

- Persistent EDMA testnet (chain 741) running 24/7 — not a local Docker devnet that resets

- Blockscout explorer at explorer.edma.app showing blocks, transactions, contracts

- Public RPC at rpc.edma.app accepting wallet connections

- All 12 smart contracts deployed to the persistent testnet with verified source code

- First test transaction: EDSD.mint → EDSD.lock → evaluateClaim → settleTrancheOnPass

- All 6 new repos created on GitHub

Starting state: Devnet runs locally in Docker (ops-bedrock). Contracts compiled and tested locally. Design system and explorer mockup approved. Everything is on localhost — nothing is publicly accessible.

End state: A publicly accessible testnet chain with a block explorer anyone can visit, an RPC endpoint any wallet can connect to, and verified contracts showing real PoV settlement transactions.

## Prerequisites (do these Sunday night)

- Cloud server provisioned — minimum 4 vCPU, 16GB RAM, 500GB SSD (AWS c5.xlarge, Hetzner CPX41, or similar)

- Domain DNS configured: explorer.edma.app, rpc.edma.app pointed to server IP

- SSL certificates ready (Let's Encrypt via certbot or Cloudflare proxy)

- Docker + Docker Compose installed on server

- GitHub repos created: edma-explorer, edma-bridge, edma-rpc, edma-faucet, edma-testnet, edma-mainnet

# Day-by-Day Plan

| MONDAY — March 17 ¦ Persistent testnet chain live |  |  |  |  |
| --- | --- | --- | --- | --- |
| Time | Task | Output | Blocked by | Done |
| Morning — Boot the chain |  |  |  |  |
| 09:00 | Clone optimism monorepo to cloud server, checkout pinned commit | Repo on server | Server ready | ☐ |
| 09:30 | Build Foundry from exact commit (143abd6a) on server | foundry binary | Repo cloned | ☐ |
| 10:00 | Apply svm-rs-builds patch (HashSet dedup for Solc 0.8.31) | Patched build.rs | Foundry built | ☐ |
| 10:30 | Run devnet init: generate genesis with chain ID 741 | Genesis state-dump-741 | Patch applied | ☐ |
| 11:00 | Configure docker-compose for persistent data volumes (not ephemeral) | docker-compose.yml | Genesis ready | ☐ |
| 11:30 | Export env vars (DGF_ADDRESS, DG_TYPE, SEQUENCER_BATCH_INBOX) | .env file | Compose config | ☐ |
| 12:00 | docker compose up — boot L1 + L2 + op-node + batcher + proposer | Chain producing blocks | Env vars set | ☐ |
| Afternoon — Verify + harden |  |  |  |  |
| 13:00 | Verify chain ID 741: cast chain-id --rpc-url localhost:9545 | Returns 0x2e5 | Chain running | ☐ |
| 13:30 | Verify blocks advancing every 2 seconds | Block height increasing | Chain ID ok | ☐ |
| 14:00 | Set up systemd service for auto-restart on server reboot | edma-testnet.service | Blocks advancing | ☐ |
| 14:30 | Configure Nginx reverse proxy: rpc.edma.app → localhost:9545 | Nginx config | systemd ready | ☐ |
| 15:00 | Enable SSL via certbot for rpc.edma.app | HTTPS working | Nginx running | ☐ |
| 15:30 | Test external connection: cast chain-id --rpc-url https://rpc.edma.app | Returns 0x2e5 remotely | SSL active | ☐ |
| 16:00 | Add MetaMask network: EDMA Testnet, chain 741, rpc.edma.app | Wallet connects | RPC public | ☐ |
| 16:30 | Send test ETH transfer between two accounts via public RPC | TX confirmed on chain | Wallet connected | ☐ |
| End of day checkpoint |  |  |  |  |
| 17:00 | ✓ Chain 741 live, blocks every 2s, rpc.edma.app public, MetaMask connects | DAY 1 COMPLETE | — | ☐ |
| TUESDAY — March 18 ¦ Smart contracts on testnet |  |  |  |  |
| Time | Task | Output | Blocked by | Done |
| Morning — Deploy contracts |  |  |  |  |
| 09:00 | SSH to server, clone edma-contracts repo | Repo on server | Chain running | ☐ |
| 09:30 | npm install in packages/contracts | Dependencies installed | Repo cloned | ☐ |
| 10:00 | Update hardhat.config.js: edma_testnet network → rpc.edma.app | Config updated | npm done | ☐ |
| 10:30 | Run deployment script: npx hardhat run script/Deploy.s.js --network edma_testnet | 12 contracts deployed | Config ready | ☐ |
| 11:00 | Save all deployed addresses to deployments/testnet/addresses.json | addresses.json | Deploy done | ☐ |
| 11:30 | Verify each contract responds: cast call <address> on each | All 12 respond | Addresses saved | ☐ |
| Afternoon — Verify source + test |  |  |  |  |
| 13:00 | Flatten contract source for each of the 12 contracts | 12 flattened .sol files | Contracts live | ☐ |
| 13:30 | Upload flattened source to Blockscout for verification (prep for tomorrow) | Verification ready | Flattened | ☐ |
| 14:00 | Run test suite against testnet: npx hardhat test --network edma_testnet | All tests pass | Contracts live | ☐ |
| 14:30 | Fix any test failures specific to testnet timing/gas | Tests green | Test run | ☐ |
| 15:00 | Register test attestor: call AttestorRegistry.register() | Attestor registered | Tests pass | ☐ |
| 15:30 | Set PoV schema for ON_BOARD milestone: call PoVGate.setSchema() | Schema configured | Attestor registered | ☐ |
| 16:00 | Fund test buyer: EDSD.mint(100000) to test address | 100K EDSD minted | Schema set | ☐ |
| 16:30 | Lock EDSD for test order: EDSD.lock() for ON_BOARD milestone | EDSD locked | EDSD minted | ☐ |
| End of day checkpoint |  |  |  |  |
| 17:00 | ✓ 12 contracts on testnet, test attestor, schema, funded order ready | DAY 2 COMPLETE | — | ☐ |
| WEDNESDAY — March 19 ¦ Block explorer live |  |  |  |  |
| Time | Task | Output | Blocked by | Done |
| Morning — Blockscout deploy |  |  |  |  |
| 09:00 | Clone Blockscout repo, checkout stable release | Blockscout repo | Server ready | ☐ |
| 09:30 | Configure docker-compose-no-build.yml for EDMA testnet RPC | Config pointing to L2 | Repo cloned | ☐ |
| 10:00 | Set env: CHAIN_ID=741, NETWORK=EDMA, SUBNETWORK=Testnet | Env configured | Compose config | ☐ |
| 10:30 | docker compose up blockscout (indexer + frontend + DB) | Blockscout indexing | Env set | ☐ |
| 11:00 | Wait for full sync — watch logs until caught up to head | Fully synced | Compose up | ☐ |
| 11:30 | Verify: blocks, transactions, addresses appearing in UI | Data visible | Synced | ☐ |
| Afternoon — EDMA branding + contract verification |  |  |  |  |
| 13:00 | Replace Blockscout logo with EDMA logo (E mark, both themes) | EDMA branding | Blockscout live | ☐ |
| 13:30 | Set primary color to #050443, accent to #F5A410 in Blockscout config | Brand colors applied | Logo replaced | ☐ |
| 14:00 | Configure Nginx: explorer.edma.app → Blockscout container | Nginx proxy | Branding done | ☐ |
| 14:30 | Enable SSL for explorer.edma.app | HTTPS working | Nginx running | ☐ |
| 15:00 | Verify contract source code on explorer (12 contracts) | Green checkmarks | SSL active | ☐ |
| 15:30 | Test: search by tx hash, block number, contract address | All searches work | Sources verified | ☐ |
| 16:00 | Verify decoded method names visible (evaluateClaim, settleTrancheOnPass) | Methods decoded | Search works | ☐ |
| 16:30 | Test on mobile — explorer loads, tables readable | Mobile OK | Desktop verified | ☐ |
| End of day checkpoint |  |  |  |  |
| 17:00 | ✓ explorer.edma.app live, EDMA branded, 12 contracts verified | DAY 3 COMPLETE | — | ☐ |
| THURSDAY — March 20 ¦ First PoV settlement on testnet |  |  |  |  |
| Time | Task | Output | Blocked by | Done |
| Morning — Execute the full deal flow |  |  |  |  |
| 09:00 | Create test order: configureMilestone (4 milestones, 25% each) | Order configured | Contracts ready | ☐ |
| 09:30 | Fund escrow: EDSD.mint(100000) + EDSD.lock (x4 milestones) | $100K locked | Order created | ☐ |
| 10:00 | Submit ON_BOARD claim with EIP-712 attestor signature | evaluateClaim TX | EDSD locked | ☐ |
| 10:30 | Verify PASS: check GatePass event in explorer | GatePass visible | Claim submitted | ☐ |
| 11:00 | Settle: settleTrancheOnPass for ON_BOARD | Settlement TX | PASS confirmed | ☐ |
| 11:30 | Verify on explorer: EMTMinted, MilestoneSettled, EDMBurned, ReceiptEmitted | 5 events decoded | Settled | ☐ |
| Afternoon — Complete all milestones + document |  |  |  |  |
| 13:00 | Submit + settle CUSTOMS milestone (same flow) | Milestone 2 settled | ON_BOARD done | ☐ |
| 13:30 | Submit + settle ARRIVAL_QA milestone (2 attestors required) | Milestone 3 settled | CUSTOMS done | ☐ |
| 14:00 | Submit + settle DELIVERY milestone (final tranche) | Milestone 4 settled | ARRIVAL_QA done | ☐ |
| 14:30 | Verify: all EDSD released, all fees recorded, EDM burned | Full deal complete | All settled | ☐ |
| 15:00 | Screenshot full deal on explorer: all TXs, events, internal calls | Screenshots saved | Deal complete | ☐ |
| 15:30 | Write test corridor report: TX hashes, gas costs, timing | Test report doc | Screenshots | ☐ |
| 16:00 | Mint test ETT (10 kWh): ETT.mint with test device evidence | ETT minted | Contracts ready | ☐ |
| 16:30 | Mint test Certificate from 100 ETTs: CertificateNFT.mint | Certificate NFT minted | ETT minted | ☐ |
| End of day checkpoint |  |  |  |  |
| 17:00 | ✓ Full 4-milestone deal settled, ETT+Certificate minted, all visible on explorer | DAY 4 COMPLETE | — | ☐ |
| FRIDAY — March 21 ¦ Polish, document, announce |  |  |  |  |
| Time | Task | Output | Blocked by | Done |
| Morning — Repos + documentation |  |  |  |  |
| 09:00 | Initialize all 6 GitHub repos with README, LICENSE, .gitignore | 6 repos ready | Repos created | ☐ |
| 09:30 | edma-testnet: push docker-compose, .env template, setup instructions | Testnet repo live | Repos init | ☐ |
| 10:00 | edma-explorer: push Blockscout config, branding assets, docker-compose | Explorer repo live | Testnet repo | ☐ |
| 10:30 | edma-rpc: push Nginx config, SSL setup, health check script | RPC repo live | Explorer repo | ☐ |
| 11:00 | Update docs.edma.app: testnet info, RPC endpoint, chain ID, contract addresses | Docs updated | All repos | ☐ |
| 11:30 | Create EDMA testnet getting-started guide: add network, get test tokens, send TX | Guide published | Docs updated | ☐ |
| Afternoon — Health checks + Week 2 prep |  |  |  |  |
| 13:00 | Uptime check: chain, explorer, RPC all responding | All green | Everything live | ☐ |
| 13:30 | Set up basic monitoring: simple cron that checks block height advancing | Monitor active | Uptime OK | ☐ |
| 14:00 | Test: external user (phone, different network) can add chain + see explorer | External access OK | Monitor active | ☐ |
| 14:30 | Create Week 2 task backlog: Bridge UI, Faucet, contract proxies | Week 2 backlog | External OK | ☐ |
| 15:00 | Identify Blockscout customization needs for EDMA event decoding | Custom indexer spec | Explorer live | ☐ |
| 15:30 | Research audit firms: timeline, cost, scope for 12 contracts | Audit shortlist | — | ☐ |
| 16:00 | Push all final code, tag release: v0.1.0-testnet | Git tag pushed | All code pushed | ☐ |
| End of day checkpoint |  |  |  |  |
| 17:00 | ✓ 6 repos live, docs updated, testnet stable 24h, ready for Week 2 | WEEK 1 COMPLETE | — | ☐ |

# Week 1 Success Criteria

All of these must be true by Friday 17:00:

| Criteria | Verification | Status |
| --- | --- | --- |
| rpc.edma.app returns chain ID 741 | cast chain-id | ☐ |
| Blocks advancing every 2 seconds for 24+ hours | Explorer block list | ☐ |
| explorer.edma.app shows blocks, TXs, addresses | Browser visit | ☐ |
| Explorer shows EDMA branding (logo, colors) | Visual check | ☐ |
| 12 contracts deployed with verified source code | Explorer contract pages | ☐ |
| MetaMask can connect to EDMA Testnet | Add network + send TX | ☐ |
| Full 4-milestone deal settled on-chain | Settlement TXs on explorer | ☐ |
| GatePass, Receipt, EDMBurned events visible and decoded | Explorer event logs | ☐ |
| ETT minted and CertificateNFT minted on testnet | Token tracker | ☐ |
| 6 GitHub repos created and initialized | github.com/devedma | ☐ |
| Chain survives server reboot (systemd auto-restart) | Reboot + check | ☐ |
| External access works (phone, different network) | Mobile test | ☐ |

# Quick Reference — Key Commands

### Server Setup

ssh root@<server-ip>

apt update && apt install -y docker.io docker-compose-v2 nginx certbot python3-certbot-nginx

### Chain Boot

cd ~/edma-testnet && docker compose up -d

cast chain-id --rpc-url http://localhost:9545  # Should return 0x2e5 (741)

cast block-number --rpc-url http://localhost:9545  # Should increase every 2s

### Contract Deploy

cd ~/edma-contracts/packages/contracts

npx hardhat run script/Deploy.s.js --network edma_testnet

### Test Settlement

# These calls use the SDK or direct cast calls

cast send <EDSD> 'mint(address,uint256)' <buyer> 100000e6 --rpc-url https://rpc.edma.app --private-key <key>

cast send <SettlementController> 'configureMilestone(...)' ... --rpc-url https://rpc.edma.app

cast send <PoVGate> 'evaluateClaim(...)' ... --rpc-url https://rpc.edma.app

### Explorer

cd ~/edma-explorer && docker compose up -d

# Blockscout UI at http://localhost:4000

# Nginx proxies explorer.edma.app → localhost:4000

### Key Addresses (from devnet — will be different on persistent testnet)

Deployer: 0xf39Fd6e51aad88F6F4ce6aB8827279cffFb92266

Key: 0xac0974bec39a17e36ba4a6b4d238ff944bacb478cbed5efcae784d7bf4f2ff80

(NEVER use this key on mainnet — this is a well-known test key)

# Week 1 Risks

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Foundry build fails on server (different arch/OS) | Day 1 slips to Day 2 | Use exact same Rust 1.80.0 + commit. Pre-build on identical container. |
| Blockscout won't sync with OP Stack L2 | Day 3 blocked | Use Blockscout optimism-specific docker config. Fallback: Otterscan. |
| Server runs out of disk (L1 state growth) | Chain stops | Start with 500GB. Monitor disk daily. L1 can be pruned. |
| DNS propagation delay | RPC/Explorer not reachable by name | Use Cloudflare for instant propagation. Test with IP first. |
| Contract deploy fails on testnet (gas, nonce) | Day 2 afternoon slips | Pre-fund deployer with plenty of test ETH. Reset nonce if needed. |